## Overview
PRODUCT PIPELINE — OVERVIEW
What's stuck where, at a glance. All numbers below are live formulas from the Pipeline tab — edit the Pipeline, not this page.
Total products | 24
Blocked (has a blocker) | 11
Listed or marketed | 6
Stage | Count | What it means
Idea | 1 | Form not chosen yet — needs 4–5 options proposed first.
Modeled | 15 | File exists, not yet printed.
Test Printed | 2 | Real print made — check it, fix problems, then photograph it.
Photographed | 0 | Real-product photos done — ready to draft the listing.
Listed | 6 | Live on Etsy.
Marketed | 0 | Listed and promoted on social.
WHERE IT'S STUCK RIGHT NOW (from the Pipeline tab, Oct 11)
• Christmas Village: modeled, not printed or listed — blocked on the 5 raised-letter sign rebuilds. Social launch target ~Nov 1; order-by cutoff ~Dec 12.
• Haunted Town: Post Office + Chapel test printed, the other 6 modeled — all blocked on listing photos, titles, tags and prices. Halloween 2026 is home display only.
• Discount Tire: modeled, blocked on your feedback on v3m.
• Nothing is at Photographed or Marketed yet — that's the gap: finished work with no listing photos is where products are piling up.

## Pipeline
PRODUCT PIPELINE — OnBrandCraftz
One row per product. Change only the Stage column as work moves — the Overview counts update themselves. Stages in order: Idea → Modeled → Test Printed → Photographed → Listed → Marketed.
Yellow cells are yours to edit. Etsy rule: listing photos must show the real physical product — renders are social-only.
Product | Family | Stage | Next step | Blocker / waiting on | Priority | Target | Notes
Christmas Village — Complete Set (15 buildings) | Christmas Village | Modeled | Print the buildings (print weekend Oct 10–11) | Raised-letter rebuilds for 5 signs still pending — current files are Oct 3 carved-sign versions | High | ~Nov 1 launch | Gingerbread + Victorian lines. Social collage + 15-slide carousel published Oct 6; animated night-scene video awaiting approval. Not listed on Etsy yet.
Christmas Village — Inn | Christmas Village | Modeled | Rebuild with raised INN sign, then print | Waiting on raised-letter rebuild | High | ~Nov 1 | Raised-letter sign approved (INN).
Christmas Village — Santa's Workshop | Christmas Village | Modeled | Rebuild with raised sign, then print | Waiting on raised-letter rebuild | High | ~Nov 1 | Raised-letter sign approved.
Christmas Village — Toy Shop (TOYS) | Christmas Village | Modeled | Rebuild with raised TOYS sign, then print | Waiting on raised-letter rebuild | High | ~Nov 1 | Raised-letter sign approved.
Christmas Village — Sweets Shop (SWEETS) | Christmas Village | Modeled | Rebuild with raised SWEETS sign, then print | Waiting on raised-letter rebuild | High | ~Nov 1 | Raised-letter sign approved.
Christmas Village — Cocoa Shop (COCOA) | Christmas Village | Modeled | Rebuild with raised COCOA sign, then print | Waiting on raised-letter rebuild | High | ~Nov 1 | Raised-letter sign approved.
Christmas Village — Other 10 buildings | Christmas Village | Modeled | Print during Christmas print run | — | High | ~Nov 1 | Remaining gingerbread + Victorian buildings from the 15-model set. Individual names to split out as printed.
Haunted Town — Post Office | Haunted Town | Test Printed | Photograph the real print, then draft listing | Listing photos, title, tags & price still to do | Medium |  | Printed in white + a painted copy. Sign changed to raised letters after carved letters read poorly; test print of new signs — feedback pending. Home display only for Halloween 2026.
Haunted Town — Chapel | Haunted Town | Test Printed | Photograph the real print, then draft listing | Listing photos, title, tags & price still to do | Medium |  | Printed. Home display only for Halloween 2026.
Haunted Town — Bakery | Haunted Town | Modeled | Test print | — | Medium |  | Square plan, hollow for LED tea light. Not listed yet.
Haunted Town — General Store | Haunted Town | Modeled | Test print | — | Medium |  | Square plan, hollow for LED tea light. Not listed yet.
Haunted Town — Schoolhouse | Haunted Town | Modeled | Test print | — | Medium |  | Square plan, hollow for LED tea light. Not listed yet.
Haunted Town — Undertaker | Haunted Town | Modeled | Test print | — | Medium |  | Square plan, hollow for LED tea light. Not listed yet.
Haunted Town — Manor | Haunted Town | Modeled | Test print | — | Medium |  | Square plan, hollow for LED tea light. Not listed yet.
Haunted Town — Cemetery (scenery) | Haunted Town | Modeled | Test print | — | Medium |  | Scenery piece. Carved epitaphs stay as-is.
Discount Tire Store | Custom Models | Modeled | Review v3m and give feedback | Awaiting Scott's feedback on v3m (delivered Oct 7) | High |  | Traced-logo lettering, tower fixed to z=64. Watertight, hollow for tea light. Not yet approved, so not test printed.
Fairy House | Fairy / Garden | Idea | Pick a form from 4–5 design options | Design choice not yet made | Low |  | New designs need 4–5 distinct options proposed before modelling.
Digital Planner DP1026 | Digital Planners | Listed | — | — | Low |  | Live.
Digital Planner DP1027 | Digital Planners | Listed | — | — | Low |  | Live.
Digital Planner DP1028 | Digital Planners | Listed | — | — | Low |  | Live.
Digital Planner DP1029 | Digital Planners | Listed | — | — | Low |  | Live.
Digital Planners DP1030–DP1034 | Digital Planners | Modeled | Finish drafts, then list (via Frank approval) | Drafts not finished | Medium |  | 5 planners drafted, not live yet. Nothing goes to Etsy without one-tap approval in Frank.
Kawaii Sticker Packs | Stickers & Printables | Listed | — | — | Low |  | Existing products, live.
Printable Wall Art / Calendars | Stickers & Printables | Listed | — | — | Low |  | Existing products, live.

## By Family
PRODUCTS BY FAMILY AND STAGE
Family | Idea | Modeled | Test Printed | Photographed | Listed | Marketed | Total
Christmas Village | 0 | 7 | 0 | 0 | 0 | 0 | 7
Haunted Town | 0 | 6 | 2 | 0 | 0 | 0 | 8
Custom Models | 0 | 1 | 0 | 0 | 0 | 0 | 1
Fairy / Garden | 1 | 0 | 0 | 0 | 0 | 0 | 1
Digital Planners | 0 | 1 | 0 | 0 | 4 | 0 | 5
Stickers & Printables | 0 | 0 | 0 | 0 | 2 | 0 | 2
Total | 1 | 15 | 2 | 0 | 6 | 0 | 24

## How to Use
HOW TO USE THIS TRACKER
1. Work in the Pipeline tab. One row per product.
2. When work moves, change the Stage cell (tap it — there's a dropdown): Idea → Modeled → Test Printed → Photographed → Listed → Marketed. Use the furthest stage actually finished.
3. Keep Next step to the single next action, and Blocker to what's actually stopping it (write — when nothing is).
4. Overview and By Family update themselves from formulas — don't type numbers there.
5. Add a product: add a row at the bottom of the Pipeline list. The Overview totals count rows 5–28; if you go past that, tell Benson and the ranges get extended.
6. Photographed means real-product photos. Etsy listings must show the real physical product — renders and AI images are for Instagram/Threads only.
7. Nothing publishes to Etsy from this sheet. Listings still go through your one-tap approval in Frank's Action Center.
Starting point (Oct 11, 2026): stages were filled in from what's known — Christmas Village modeled with print planned Oct 10–11 and 5 raised-letter rebuilds pending; Haunted Town Post Office and Chapel printed, the rest modeled; Discount Tire v3m awaiting feedback; DP1026–DP1029 live and DP1030–DP1034 drafted. Correct any row that's off and the counts follow.